## Blad1
Developers | Gamelab uren per week | Werk/Baan | Role | Weken | Dagen | No weekends/1 weeks less | time axis 2016-09-05 to 2017-01-22
Arne | 14:45 | X | Planner | 13 | 105 | 58 DAGEN
Alieke | 14:45 | Vrijwilliger | Producer | 13 | 105 | 58 DAGEN
Sascha | 14:45 | X | Level Designer | 13 | 105 | 58 DAGEN
Jordi | 14:45 | 2 Banen | Lead Dev | 13 | 105 | 58 DAGEN
Artists
Rilana | 14:45 | X | Lead Art | 13 | 105 | 58 DAGEN
Janneke | 14:45 | X | Q&A | 13 | 105 | 58 DAGEN
Marc | 14:45 | 1 Baan | UX | 13 | 105 | 58 DAGEN
Developers | Gamelab uren per week | Werk/Baan | Role | Weken | Dagen | No weekends/1 weeks less | time axis 2016-09-05 to 2017-01-22
Arne | 14:45 | X | Planner | 13 | 105 | 58 DAGEN | 2016-09-05: XXXXXXX; 2016-09-06: XXXXXXX; 2016-09-07: XXXXXXX; 2016-09-08: XXXXXXX; 2016-09-09: XXXXXXX; 2016-09-10: XXXXXXX; 2016-09-11: XXXXXXX; 2016-09-17: XXXXXXX; 2016-09-18: XXXXXXX; 2016-09-19: Begin; 2016-09-24: XXXXXXX; 2016-09-25: XXXXXXX; 2016-10-01: XXXXXXX; 2016-10-02: XXXXXXX; 2016-10-08: XXXXXXX; 2016-10-09: XXXXXXX; 2016-10-15: XXXXXXX; 2016-10-16: XXXXXXX; 2016-10-22: XXXXXXX; 2016-10-23: XXXXXXX; 2016-10-24: XXXXXXX; 2016-10-25: XXXXXXX; 2016-10-26: XXXXXXX; 2016-10-27: XXXXXXX; 2016-10-28: XXXXXXX; 2016-10-29: XXXXXXX; 2016-10-30: XXXXXXX; 2016-11-05: XXXXXXX; 2016-11-06: XXXXXXX; 2016-11-12: XXXXXXX; 2016-11-13: XXXXXXX; 2016-11-19: XXXXXXX; 2016-11-20: XXXXXXX; 2016-11-26: XXXXXXX; 2016-11-27: XXXXXXX; 2016-12-03: XXXXXXX; 2016-12-04: XXXXXXX; 2016-12-10: XXXXXXX; 2016-12-11: XXXXXXX; 2016-12-17: XXXXXXX; 2016-12-18: XXXXXXX; 2016-12-24: XXXXXXX; 2016-12-25: XXXXXXX; 2016-12-26: XXXXXXX; 2016-12-27: XXXXXXX; 2016-12-28: XXXXXXX; 2016-12-29: XXXXXXX; 2016-12-30: XXXXXXX; 2016-12-31: XXXXXXX; 2017-01-01: XXXXXXX; 2017-01-02: XXXXXXX; 2017-01-03: XXXXXXX; 2017-01-04: XXXXXXX; 2017-01-05: XXXXXXX; 2017-01-06: XXXXXXX; 2017-01-07: XXXXXXX; 2017-01-08: XXXXXXX; 2017-01-14: XXXXXXX; 2017-01-15: XXXXXXX; 2017-01-21: XXXXXXX; 2017-01-22: XXXXXXX
Alieke | 14:45 | Vrijwilliger | Producer | 13 | 105 | 58 DAGEN | 2016-09-17: Sprint 1; 2016-11-05: Sprint 2; 2017-01-22: Sprint 3
Sascha | 14:45 | X | Level Designer | 13 | 105 | 58 DAGEN | 2016-09-19: WEEK 1; 2016-09-26: WEEK2; 2016-10-03: WEEK 3; 2016-10-10: WEEK 4; 2016-10-17: WEEK 5; 2016-10-31: WEEK 6; 2016-11-07: WEEK 7; 2016-11-14: WEEK 8; 2016-11-21: WEEK 9; 2016-11-28: WEEK 10; 2016-12-05: WEEK 11; 2016-12-12: WEEK 12; 2016-12-19: WEEK 13; 2017-01-09: WEEK 14; 2017-01-16: WEEK 15
Jordi | 14:45 | 2 Banen | Lead Dev | 13 | 105 | 58 DAGEN
Artists
Rilana | 14:45 | X | Lead Art | 13 | 105 | 58 DAGEN
Janneke | 14:45 | X | Q&A | 13 | 105 | 58 DAGEN
Marc | 14:45 | 1 Baan | UX | 13 | 105 | 58 DAGEN

## Blad2
|  | Object | Code | Opmerking | Tijdsinschatting | Priority | Maker | Status | In Trello
2D
| Textures | 2D_TXT
|  | Futon | 2D_TXT_FUTON |  |  | B | Rilana |  | X
|  | Crack Wall | 2D_TXT_CRACKWALL |  |  | A | Rilana |  | X
|  | Broken Futon | 2D_TXT_BFUTON |  |  | C | Rilana
|  | Table | 2D_TXT_TABLE |  |  | B | Rilana |  | X
|  | Roof | 2D_TXT_ROOF |  |  | A | Rilana |  | X
|  | Door Wall | 2D_TXT_DOORWALL |  |  | A | Rilana |  | X
|  | Chalkboard | 2D_TXT_CHALKB |  |  | B |  |  | X
|  | Paper | 2D_TXT_PAPER |  |  | C | Marc
|  | Wall | 2D_TXT_WALL |  |  | A | Rilana |  | X
|  | Fence 1 | 2D_TXT_FENCE1 |  |  | A | Marc |  | X
|  | Kitchen | 2D_TXT_KITCH |  |  | A | Janneke |  | X
|  | Pot | 2D_TXT_POT |  |  | C | Janneke
|  | Pan | 2D_TXT_PAN |  |  | C | Janneke
|  | Chopsticks | 2D_TXT_CHOPS |  |  | C | Janneke
|  | Bowl | 2D_TXT_BOWL |  |  | C | Janneke
|  | KitchenTable | 2D_TXT_KITCHTABLE |  |  | B | Janneke |  | X
|  | Kitchen Futon | 2D_TXT_KITCHFUTON |  |  | B | Janneke |  | X
|  | Thrashcan | 2D_TXT_THRASH |  |  | C | Janneke
|  | BabyKappa | 2D_TXT_BABYKAPPA |  |  | A | Janneke |  | X
|  | Kappa | 2D_TXT_KAPPA |  |  | A | Janneke |  | X
|  | BossKappa | 2D_TXT_BOSSKAPPA |  |  | A | Marc |  | X
|  | Wood Box | 2D_TXT_BOX |  |  | B | Marc |  | X
|  | Ceiling Hole | 2D_TXT_CEILINGHOLE |  |  | A | Rilana |  | X
|  | Rope | 2D_TXT_ROPE |  |  | B | Marc |  | X
|  | Hook | 2D_TXT_HOOK |  |  | B | Marc |  | X
|  | Ring Hook | 2D_TXT_RINGHOOK | Grappling Hook hits ring to grapple |  | A | Marc |  | X
|  | Blade | 2D_TXT_BLADE |  |  | B | Janneke |  | X
|  | Half Blade | 2D_TXT_HALFBLADE |  |  | C | Janneke
|  | Broken Box | 2D_TXT_BBOX |  |  | B | Marc |  | X
|  | Wood Dummy | 2D_TXT_WDUMMY |  |  | C | Rilana |  | X
|  | Mats | 2D_TXT_MATS |  |  | B | Rilana |  | X
|  | Broken Armor | 2D_TXT_BARMOR |  |  | C
|  | Roof Crack | 2D_TXT_ROOFCRACK |  |  | A | Rilana |  | X
|  | Extra Heart | 2D_TXT_EXTRAHP |  |  | B | Janneke |  | X
|  | Tree 1 | 2D_TXT_TREE1 |  |  | A | Marc |  | X
|  | Tree 2 | 2D_TXT_TREE2 |  |  | C | Marc |  | X
|  | Tree 3 | 2D_TXT_TREE3 |  |  | C | Marc
|  | Bush | 2D_TXT_BUSH |  |  | A | Janneke |  | X
|  | Grass 1 | 2D_TXT_GRASS1 |  |  | A | Janneke |  | X
|  | Grass 2 | 2D_TXT_GRASS2 |  |  | C | Janneke
|  | Stone 1 | 2D_TXT_STONE1 |  |  | A | Marc |  | X
|  | Stone 2 | 2D_TXT_STONE2 |  |  | C | Marc
|  | Terrain | 2D_TXT_TERRAIN |  |  | A | Sascha |  | X
|  | Background 1 | 2D_TXT_BACKG1 |  |  | A |  |  | X
|  | Background 2 | 2D_TXT_BACKG2 |  |  | B |  |  | X
|  | Background 3 | 2D_TXT_BACKG3 |  |  | C
|  | Cabin | 2D_TXT_CABIN |  |  | A | Janneke |  | X
|  | Wood Fence | 2D_TXT_WOODFENCE |  |  | B | Janneke |  | X
|  | Falllen Tree Trunk | 2D_TXT_FALLTREETRUNK |  |  | A | Marc |  | X
|  | Tree Trunk | 2D_TXT_TREETRUNK |  |  | C | Marc
|  | Boulder1 | 2D_TXT_BOULDER1 |  |  | A | Marc |  | X
|  | Shurikens | 2D_TXT_SHURIKEN |  |  | A | Marc |  | X
|  | Old Man | 2D_TXT_OLDMAN |  |  | B | Marc |  | X
|  | Sides Bridge | 2D_TXT_SIDEBRIDGE |  |  | A | Rilana |  | X
|  | Middle Bridge | 2D_TXT_MIDDLEBRIDGE |  |  | A | Rilana |  | X
|  | Terrain Grass 1 | 2D_TXT_TERRAINGRASS1 |  |  | A | XXXXXX |  | X
|  | Terrain Grass 2 | 2D_TXT_TERRAINGRASS2 |  |  | C | XXXXXX
|  | Terrain Wet Grass | 2D_TXT_TERRAINWETGRASS |  |  | B | XXXXXX |  | X
|  | Bamboo | 2D_TXT_BAMBOO |  |  | C | Marc
|  | Terrain Hills | 2D_TXT_TERRAINHILLS |  |  | A | XXXXXX |  | X
|  | Dirt Water Floor | 2D_TXT_DIRTWATERFLOOR |  |  | C | XXXXXX
|  | Sand Shore | 2D_TXT_SANDSHORE |  |  | B | XXXXXX |  | X
|  | Walkway | 2D_TXT_WALKWAY |  |  | A | XXXXXX |  | X
|  | Footprint Kappa | 2D_TXT_FOOTPRINT |  |  | B | XXXXXX |  | X
|  | Lantern | 2D_TXT_LANTERN |  |  | A | Janneke |  | X
|  | Terrain 1 | 2D_TXT_TERRAIN1 |  |  | A | XXXXXX |  | X
|  | Terrain 3 | 2D_TXT_TERRAIN3 |  |  | A | XXXXXX |  | X
|  | Bag | 2D_TXT_BAG |  |  | B | Rilana |  | X
|  | Smoke Bomb | 2D_TXT_SMOKEBOMB |  |  | A | Rilana |  | X
|  | Boulder2 | 2D_TXT_BOULDER2 | CRACKED |  | B | Marc |  | X
|  | Shrine | 2D_TXT_SHRINE |  |  | A | Janneke |  | X
|  | Background Sea Waves | 2D_TXT_BGSEAWAVES |  |  | C | XXXXXX
|  | Background Sunset | 2D_TXT_BGSUNSET |  |  | B | XXXXXX |  | X
|  | Background Moon | 2D_TXT_BGMOON |  |  | C | XXXXXX
|  | Background Forest | 2D_TXT_BGFOREST |  |  | B | XXXXXX |  | X
|  | Background Hills | 2D_TXT_BGHILLS |  |  | A | XXXXXX |  | X
|  | Background Underground | 2D_TXT_BGUNDERGROUND |  |  | A | XXXXXX |  | X
S |  | Smoke | 2D_TXT_SMOKE |  |  | B | XXXXXX |  | X
|  | MC Model | 2D_TXT_MCMODEL |  |  | A | Rilana |  | X
|  | Portrait Old Man | 2D_TXT_OLDMANPORTRAIT |  |  | C | XXXXXX
|  | Portrait Player | 2D_TXT_PLAYERPORTRAIT |  |  | C | XXXXXX
|  | Rope | 2D_TXT_ROPE |  |  | A | Marc
|  | Hook | 2D_TXT_HOOK |  |  | A | Marc
3D
| Props | 3D_PRP
|  | Futon | 3D_PRP_FUTON |  |  | B | Rilana |  | X
|  | Table | 3D_PRP_TABLE |  |  | B | Rilana |  | X
|  | Broken Futon | 3D_PRP_BFUTON |  |  | C | Rilana
|  | Paper | 3D_PRP_PAPER |  |  | C | Marc
|  | Fence1 | 3D_PRP_FENCE1 |  |  | A | Marc |  | X
|  | Pot | 3D_PRP_POT |  |  | C | Janneke
|  | Pan | 3D_PRP_PAN |  |  | C | Janneke
|  | ChopSticks | 3D_PRP_CHOPS |  |  | C | Janneke
|  | Bowl | 3D_PRP_BOWL |  |  | C | Janneke
|  | Kitchen Table | 3D_PRP_KITCHTABLE |  |  | B | Janneke |  | X
|  | Kitchen Futon | 3D_PRP_KITCHFUTON |  |  | B | Janneke |  | X
|  | Thrashcan | 3D_PRP_THRASH |  |  | C | Janneke
|  | Wood Box | 3D_PRP_BOX |  |  | B | Marc |  | X
|  | Broken Box | 3D_PRP_BBOX |  |  | B | Marc |  | X
|  | Wood Dummy | 3D_PRP_WDUMMY |  |  | B | Rilana |  | X
|  | Mats | 3D_PRP_MATS |  |  | B | Rilana |  | X
| Environment | 3D_ENV
|  | Crack Wall | 3D_ENV_CRACKWALL |  |  | A | Rilana |  | X
|  | Roof | 3D_ENV_ROOF |  |  | A | Rilana |  | X
|  | ChalkBoard | 3D_ENV_CHALKB |  |  | B | … |  | X
|  | Door Wall | 3D_ENV_DOORWALL |  |  | A | Rilana |  | X
|  | Wall | 3D_ENV_WALL |  |  | A | Rilana |  | X
|  | Kitchen | 3D_ENV_KITCH |  |  | A | Janneke |  | X
|  | Stair Wall | 3D_ENV_STAIRWALL |  |  | A | Rilana |  | X
|  | Ceiling Hole | 3D_ENV_CEILINGHOLE |  |  | A | Rilana |  | X
|  | Roof Crack | 3D_ENV_ROOFCRACK |  |  | A | Rilana |  | X
|  | Tree 1 | 3D_ENV_TREE1 |  |  | A | Marc |  | X
|  | Tree 2 | 3D_ENV_TREE2 |  |  | C | Marc
|  | Tree 3 | 3D_ENV_TREE3 |  |  | C | Marc
|  | Bush | 3D_ENV_BUSH |  |  | A | Janneke |  | X
|  | Grass 1 | 3D_ENV_GRASS1 |  |  | A | Janneke |  | X
|  | Grass 2 | 3D_ENV_GRASS2 |  |  | C | Janneke
|  | Stone 1 | 3D_ENV_STONE1 | Kleine steen |  | A | Marc |  | X
|  | Stone 2 | 3D_ENV_STONE2 | Grotere steen andere vorm |  | C | Marc
|  | Terrain | 3D_ENV_TERRAIN |  |  | A | Sascha |  | X
|  | Cabin | 3D_ENV_CABIN |  |  | A | Janneke |  | X
|  | Wood Fence | 3D_ENV_WOODFENCE |  |  | B | Janneke |  | X
|  | Fallen Tree Trunk | 3D_ENV_FALLTREETRUNK |  |  | A | Marc |  | X
|  | Tree Trunk | 3D_ENV_TREETRUNK |  |  | C | Marc
|  | Boulder1 | 3D_ENV_BOULDER1 |  |  | A | Marc |  | X
|  | WATER | 3D_ENV_WATER |  |  | A | Sascha |  | X
|  | Sides Bridge | 3D_ENV_SIDEBRIDGE |  |  | A | Rilana |  | X
|  | Middle Bridge | 3D_ENV_MIDDLEBRIDGE |  |  | A | Rilana |  | X
|  | Bamboo | 3D_ENV_BAMBOO |  |  | C | Marc
|  | Lantern | 3D_ENV_LANTERN |  |  | A | Janneke |  | X
|  | Boulder2 | 3D_ENV_BOULDER2 | CRACKED |  | B | Marc
|  | Shrine | 3D_ENV_SHRINE |  |  | A | Janneke |  | X
| Interactives | 3D_INT
|  | Hook | 3D_INT_GRAPPLINGHOOK |  |  | A | Marc
|  | Ring Hook | 3D_INT_RINGHOOK | Grappling Hook hits ring to grapple |  | A | Marc |  | X
|  | Blade | 3D_INT_BLADE |  |  | B | Janneke |  | X
|  | Half Blade | 3D_INT_HBLADE |  |  | C | Janneke
|  | Broken Armor | 3D_INT_BARMOR |  |  | C | …
|  | Extra Heart | 3D_INT_EXTRAHP |  |  | B | Janneke |  | X
|  | Shuriken | 3D_INT_SHURIKEN |  |  | A | Marc |  | X
|  | Bag | 3D_INT_BAG |  |  | B | Rilana |  | X
|  | Smoke Bomb | 3D_INT_SMOKEBOMB |  |  | A | Rilana |  | X
| Characters | 3D_CHAR
|  | BabyKappa | 3D_CHAR_BABYKAPPA |  |  | A | Janneke |  | X
|  | Kappa | 3D_CHAR_KAPPA |  |  | A | Janneke |  | X
|  | BossKappa | 3D_CHAR_BOSSKAPPA |  |  | A | Marc |  | X
|  | Old Man | 3D_CHAR_OLDMAN |  |  | C | Marc
|  | MC Model | 3D_CHAR_MCMODEL |  |  | A | Rilana |  | X
4U | Unwrap
| Props | 4U_PRP
|  | Broken Futon | 4U_PRP_BFUTON |  |  | C | Rilana
|  | Paper | 4U_PRP_PAPER |  |  | C | Marc
|  | Fence1 | 4U_PRP_FENCE1 |  |  | A | Marc |  | X
|  | Futon | 4U_PRP_FUTON |  |  | B | Rilana
|  | Pot | 4U_PRP_POT |  |  | C | Janneke
|  | Pan | 4U_PRP_PAN |  |  | C | Janneke
|  | ChopSticks | 4U_PRP_CHOPS |  |  | C | Janneke
|  | Bowl | 4U_PRP_BOWL |  |  | C | Janneke
|  | Kitch Table | 4U_PRP_KITCHTABLE |  |  | B | Janneke
|  | Kitchen Futon | 4U_PRP_KITCHFUTON |  |  | B | Janneke
|  | Thrashcan | 4U_PRP_THRASH |  |  | C | Janneke
|  | Wood Box | 4U_PRP_BOX |  |  | B | Marc
|  | Broken Box | 4U_PRP_BBOX |  |  | B | Marc
|  | Wood Dummy | 4U_PRP_WDUMMY |  |  | B | Rilana
|  | Mats | 4U_PRP_MATS |  |  | B | Rilana
| Environment | 4U_ENV
|  | Crack Wall | 4U_ENV_CRACKWALL |  |  | A | Rilana |  | X
|  | Roof | 4U_ENV_ROOF |  |  | A | Rilana |  | X
|  | Door Wall | 4U_ENV_DOORWALL |  |  | A | Rilana |  | X
|  | Chalkboard | 4U_ENV_CHALKB |  |  | B | … |  | X
|  | Wall | 4U_ENV_WALL |  |  | A | Rilana |  | X
|  | Stair Wall | 4U_ENV_STAIRWALL |  |  | A | Rilana |  | X
|  | Kitchen | 4U_ENV_KITCH |  |  | A | Janneke |  | X
|  | Ceiling Hole | 4U_ENV_CEILINGHOLE |  |  | A | Rilana |  | X
|  | Roof Crack | 4U_ENV_ROOFCRACK |  |  | A | Rilana |  | X
|  | Tree 1 | 4U_ENV_TREE1 |  |  | A | Marc |  | X
|  | Tree 2 | 4U_ENV_TREE2 |  |  | C | Marc
|  | Tree 3 | 4U_ENV_TREE3 |  |  | C | Marc
|  | Bush | 4U_ENV_BUSH |  |  | A | Janneke |  | X
|  | Grass 1 | 4U_ENV_GRASS1 |  |  | A | Janneke |  | X
|  | Grass 2 | 4U_ENV_GRASS2 |  |  | C | Janneke
|  | Stone 1 | 4U_ENV_STONE1 |  |  | A | Marc |  | X
|  | Stone 2 | 4U_ENV_STONE2 |  |  | C | Marc
|  | Terrain | 4U_ENV_TERRAIN |  |  | A | Sascha |  | X
|  | Cabin | 4U_ENV_CABIN |  |  | A | Janneke |  | X
|  | Wood Fence | 4U_ENV_WOODFENCE |  |  | B | Janneke |  | X
|  | Fallen Tree Trunk | 4U_ENV_FALLTREETRUNK |  |  | A | Sascha |  | X
|  | Tree Trunk | 4U_ENV_TREETRUNK |  |  | C
|  | Boulder 1 | 4U_ENV_BOULDER1 |  |  | A |  |  | X
|  | Sides Bridge | 4U_ENV_SIDEBRIDGE |  |  | A |  |  | X
|  | Middle Bridge | 4U_ENV_MIDDLEBRIDGE |  |  | A |  |  | X
|  | Bamboo | 4U_ENV_BAMBOO |  |  | C
|  | Lantern | 4U_ENV_LANTERN |  |  | A |  |  | X
|  | Boulder 2 | 4U_ENV_BOULDER2 | CRACKED |  | B
|  | Shrine | 4U_ENV_SHRINE |  |  | A |  |  | X
| Interactives | 4U_INT
|  | Grappling | 4U_INT_GRAPPLINGHOOK |  |  | A
|  | Ring Hook | 4U_INT_RINGHOOK | Grappling Hook hits ring to grapple |  | A |  |  | X
|  | Broken Armor | 4U_INT_BARMOR |  |  | B
|  | Extra Heart | 4U_INT_EXTRAHP |  |  | B
|  | Shurikens | 4U_INT_SHURIKEN |  |  | A |  |  | X
|  | Bag | 4U_INT_BAG |  |  | B
|  | Smoke Bomb | 4U_INT_SMOKEBOMB |  |  | A |  |  | X
Characters
|  | BabyKappa | 4U_CHAR_BABYKAPPA |  |  | A | Janneke |  | X
|  | Kappa | 4U_CHAR_KAPPA |  |  | A | Janneke |  | X
|  | BossKappa | 4U_CHAR_BOSSKAPPA |  |  | A | Marc |  | X
|  | Old Man | 4U_CHAR_OLDMAN |  |  | C
|  | Old Man Wife | 4U_CHAR_OLDMANWIFE |  |  | C
|  | MC Model | 4U_CHAR_MCMODEL |  |  | A | Rilana |  | X
5R | Rigging
| Characters | 5R_CHAR
|  | Kappa | 5R_CHAR_KAPPA |  |  | A | Janneke |  | X
|  | BossKappa | 5R_CHAR_BOSSKAPPA |  |  | A | Marc |  | X
|  | BabyKappa | 5R_CHAR_BABYKAPPA |  |  | A | Janneke |  | X
|  | Old Man | 5R_CHAR_OLDMAN |  |  | C | Marc
|  | Old Man Wife | 5R_CHAR_OLDMANWIFE |  |  | C | Marc
|  | MC Model | 5R_CHAR_MCMODEL |  |  | A | Rilana |  | X
6A | Animation
| Characters | 6A_CHAR
|  | MC Run | 6A_CHAR_MCRUN |  |  | C | Rilana
|  | MC Dash | 6A_CHAR_MCDASH |  |  | C | Rilana
|  | MC Shuriken Throw | 6A_CHAR_MCSHURIKENTHROW |  |  | C | Rilana
|  | MC Jump | 6A_CHAR_MCJUMP |  |  | C | Rilana
|  | MC Sneak | 6A_CHAR_MCSNEAK |  |  | C | Rilana
|  | MC Death | 6A_CHAR_MCDEATH |  |  | C | Rilana
|  | MC GrapplingHook | 6A_CHAR_GRAPPLINGHOOK |  |  | C | Rilana
|  | MC Smokebomb | 6A_CHAR_SMOKEBOMB |  |  | C | Rilana
|  | MC Idle | 6A_CHAR_MCIDLE |  |  | C | Rilana
|  | Idle 1 | 6A_CHAR_IDLE1 | Kappa 1 |  | C | Marc
|  | Idle 2 | 6A_CHAR_IDLE2 | Kappa 2 |  | C | Marc
|  | Idle 3 | 6A_CHAR_IDLE3 | Kappa 3 |  | C | Marc
|  | Sleep | 6A_CHAR_SLEEP | Kappa Sleep |  | C | Marc
|  | Attack 1 | 6A_CHAR_ATTACK1 | Kappa 1 |  | C | Marc
|  | Attack 2 | 6A_CHAR_ATTACK2 | Kappa 2 |  | C | Marc
|  | Attack 3 | 6A_CHAR_ATTACK3 | Kappa 3 |  | C | Marc
|  | Walk1 | 6A_CHAR_WALK1 | Kappa 1 |  | C | Marc
|  | Walk2 | 6A_CHAR_WALK2 | Kappa 2 |  | C | Marc
|  | Walk3 | 6A_CHAR_WALK3 | Kappa 3 |  | C | Marc
|  | Death 1 | 6A_CHAR_DEATH1 | Kappa 1 |  | C | Marc
|  | Death 2 | 6A_CHAR_DEATH2 | Kappa 2 |  | C | Marc
|  | Death 3 | 6A_CHAR_DEATH3 | Kappa 3 |  | C | Marc
7S | Sound
| BGM | BGM |  | .mp3 |  | A
|  | BGM_IntroCutscene |  |  |  | A | Jordi
|  | BGM_Level1 |  |  |  | A | Jordi
|  | BGM_Level2 |  |  |  | A | Sascha
|  | BGM_Level3 |  |  |  | A | Sascha
|  | BGM_BossFight |  |  |  | B | Sascha
|  | BGM_Ending |  |  |  | A | Jordi
|  | BGM_Credits |  |  |  | B | Jordi/Sascha
|  | BGM_MainMenu |  |  |  | A | Jordi/Sascha
|  | BGM_Chase |  |  |  | A | Jordi
| SFX_Player | SFX_Step |  | .wav |  | A
|  | SFX_Slash1 |  |  |  | A
|  | SFX_Slash2 |  |  |  | B
|  | SFX_Slash3 |  |  |  | B
|  | SFX_HitDestructible |  |  |  | A
|  | SFX_HitKappa |  |  |  | A
|  | SFX_Jump |  |  |  | A
|  | SFX_Dash |  |  |  | A
|  | SFX_Hook |  |  |  | A
|  | SFX_HookHit |  |  |  | B
|  | SFX_SmokeBomb |  |  |  | A
|  | SFX_ShurikenThrow |  |  |  | A
|  | SFX_ShurikenHitWall |  |  |  | B
|  | SFX_Die |  |  |  | A
|  | SFX_GetHit |  |  |  | A
|  | SFX_LandOnSteppingStone |  |  |  | A
|  | SFX_LandOnGround |  |  |  | A
| SFX_UI | SFX_ButtonHover |  |  |  | A
|  | SFX_ButtonPress |  |  |  | A
|  | SFX_ItemObtained |  |  |  | A
|  | SFX_HeartObtained |  |  |  | A
|  | SFX_LifeObtained |  |  |  | A
|  | SFX_OpenPauseMenu |  |  |  | A
|  | SFX_Speech |  |  |  | C
|  | SFX_QuestCompleted |  |  |  | A
|  | SFX_QuestAdded |  |  |  | A
| SFX_Enemy | SFX_Growl1 |  | .wav |  | A
|  | SFX_Growl2 |  |  |  | B
|  | SFX_BabyGrowl |  |  |  | A
|  | SFX_KappaDie |  |  |  | A
|  | SFX_BabyDie |  |  |  | A
|  | SFX_Spirit |  |  |  | B
|  | SFX_EnemyAttack |  |  |  | A
| AMB | AMB_Owls |  | .mp3 |  | B
|  | AMB_Cicadas |  |  |  | B
|  | AMB_Water |  |  |  | B
|  | AMB_Birds |  |  |  | B
8S | Script
| System | StatsManager.cs |  |  |  | A | Jordi
|  | PlayersSpawner.cs |  |  |  | A | Jordi
| Player | OptionSettings.cs |  |  |  | A | Jordi
|  | ProgressionManager.cs |  |  |  | A | Jordi
|  | QuestManager.cs |  |  |  | A | Jordi
|  | QuestClass.cs |  |  |  | A | Jordi
| UI | LoadController.cs |  |  |  | A | Jordi
|  | IntroCutscene.cs |  |  |  | A | Jordi
| Player | CameraController.cs |  |  |  | A | Jordi
|  | PlayerController.cs |  |  |  | A | Jordi
|  | PlayerSS.cs |  |  |  | A | Jordi
|  | PlayerTD.cs |  |  |  | A | Jordi
|  | CutsceneController.cs |  |  |  | A | Jordi
|  | Sword.cs |  |  |  | A | Jordi
|  | GrapplingHook.cs |  |  |  | A | Jordi
| AI | SmokeBombs.cs |  |  |  | A | Jordi
|  | Shuriken.cs |  |  |  | A | Jordi
| AI | EnemyBehaviour.cs |  |  |  | A | Alieke
|  | EnemySight.cs |  |  |  | A | Alieke
|  | BossBehaviour.cs |  |  |  | A | Alieke
|  | ChasingEnemyBehaviour.cs |  |  |  | A | Alieke
Environment
| Environment | PickUpScript.cs |  |  |  | A | Sascha
|  | InteractScript.cs |  |  |  | A | Sascha
|  | PickUpHeartsScript.cs |  |  |  | A | Sascha
|  | DestructibleScript.cs |  |  |  | A | Sascha
|  | LevelPortal.cs |  |  |  | A | Sascha
|  | SteppingStones.cs |  |  |  | A | Sascha
|  | HookScript.cs |  |  |  | A | Sascha
CellShader.shader
| UI | UIManager.cs |  |  |  | A | Arne
|  | LocationEnter.cs |  |  |  | A | Arne
|  | PauseManager.cs |  |  |  | A | Arne
|  | MainMenuManager.cs |  |  |  | A | Arne
|  | OptionsManager.cs |  |  |  | A | Arne
9P | Particle
| Environment | 9P_ENV
|  | Bling Bling | 9P_ENV_BLING |  |  | B
|  | Aurora | 9P_ENV_AURORA |  |  | B
| Interactives | 9P_INT
|  | Smoke | 9P_INT_SMOKE |  |  | B